## Capacity_8_hrs
Sprint #1: 02/14 to 02/25
Name | Daily capacity (hrs) | Sprint 1 capacity (hrs) | total sprint # of days | sprint planning (days) | sprint review/retro (days) | QA+Defects fixing+defects retesting (hrs) | Holidays/PTO (days) | Active dev days
Kumar Anagandula, Harish | 6 | 48 | 10 | 1 | 0 | 0 | 1 | 8
Geever, Vineeth Paul | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 9
Surve, Diptesh Dattaram | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Kumari, Dolly | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 9
Naresh, Parnapalli | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Begum, Tadimarri Akhila | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Para, Mohsin Hussain | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Total capacity |  | 336 |  |  | Prod Support | hrs
Actual Dev + UT |  | 126.5 |  |  | Antra | 40
Actual Dev + QA |  | 176.5 |  |  | Durga | 40
Daily scrum |  | 50 | 0.5 hrs each day for each member |  | Geever, Vineeth Paul | 80 | 1863854 | [Prod] EMA Mailbox sync issues
Bug fixes + DevOps (code review/review comments incorporation/build activities/BSA clarification) |  | 44.275 | ~ 35% of Actual Dev + UT |  | Kumari, Dolly | 80
standard buffer |  | 67.2 | ~ buffer is 20% of total capacity |  | Preeti | 40 | QA activities
Actual buffer |  | 65.225
Sprint# 2: 02/28/2022 to 03/11/2022
Name | Daily capacity | Sprint 2 capacity (hrs) | total sprint# of days | sprint planning (days) | sprint review/retro | QA+Defects fixing+defects retesting (hrs) | Holidays/PTO (days) | Active dev days
Kumar Anagandula, Harish | 6 | 54 | 10 | 1 | 0 | 0 | 0 | 9
Geever, Vineeth Paul | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 9
Surve, Diptesh Dattaram | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Kumari, Dolly | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Naresh, Parnapalli | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 9
Begum, Tadimarri Akhila | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Para, Mohsin Hussain | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Total capacity |  | 342
Actual Dev + UT |  | 136.85 |  |  | Prod Support | hrs
Actual Dev + QA |  | 202.85 |  |  | Antra | 40
Daily scrum |  | 50 | 0.5 hrs each day for each member |  | Durga | 40
Bug fixes + DevOps (code review/review comments incorporation/build activties/BSA clarification) |  | 47.8975 | ~ 35% of Actual Dev + UT |  | Geever, Vineeth Paul | 80
Standard buffer |  | 68.4 | ~ buffer is 20% of total capacity |  | Naresh, Parnapalli | 80
Actual buffer |  | 41.2525
Sprint# 3 - 03/14/2022 to 03/25/2022
Name | Daily capacity | Sprint 1 capacity (hrs) | total sprint# of days | sprint planning (days) | sprint review/retro | QA+Defects fixing+defects retesting (hrs) | Holidays/PTO (days) | Active dev days
Kumar Anagandula, Harish | 6 | 48 | 10 | 1 | 0 | 0 | 1 | 8
Geever, Vineeth Paul | 0 | 0 | 10 | 1 | 0 | 0 | 1 | 8
Surve, Diptesh Dattaram | 0 | 0 | 10 | 1 | 0 | 0 | 1 | 8
Kumari, Dolly | 8 | 48 | 10 | 1 | 0 | 0 | 3 | 6
Naresh, Parnapalli | 8 | 64 | 10 | 1 | 0 | 0 | 1 | 8
Begum, Tadimarri Akhila | 8 | 64 | 10 | 1 | 0 | 0 | 1 | 8
Para, Mohsin Hussain | 8 | 64 | 10 | 1 | 0 | 0 | 1 | 8
Total capacity |  | 288
Actual Dev + UT |  | 70.15
Actual Dev + QA |  | 134.15 |  |  | Prod Support | hrs
Daily scrum |  | 50 | 0.5 hrs each day for each member |  | Antra | 40
bug fixes + devOps (code review/review comments incorporation/build activties/BSA clarification) |  | 24.5525 | ~ 35% of Actual Dev + UT |  | Durga | 40
Standard buffer |  | 57.6 | ~ buffer is 20% of total capacity |  | Geever, Vineeth Paul | 80
Actual buffer |  | 79.2975 |  |  | Surve, Diptesh Dattaram | 80
Sprint# 4 - 03/28/2022 to 04/8/2022
Name | Daily capacity | Sprint 2 capacity (hrs) | total sprint# of days | sprint planning (days) | sprint review/retro | QA+Defects fixing+defects retesting (hrs) | Holidays/PTO (days) | Active dev days
Kumar Anagandula, Harish | 6 | 54 | 10 | 1 | 0 | 0 | 0 | 9
Geever, Vineeth Paul | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 9
Surve, Diptesh Dattaram | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Kumari, Dolly | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Naresh, Parnapalli | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 9
Begum, Tadimarri Akhila | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Para, Mohsin Hussain | 8 | 72 | 10 | 1 | 0 | 0 | 0 | 9
Total capacity |  | 342
Actual Dev + UT |  | 80.5
Actual Dev + QA |  | 102.5 |  |  | Prod Support | hrs
Daily scrum |  | 50 | 0.5 hrs each day for each member |  | Antra | 40
bug fixes + devOps (code review/review comments incorporation/build activties/BSA clarification) |  | 28.175 | ~ 35% of Actual Dev + UT |  | Durga | 40
Standard buffer |  | 68.4 | ~ buffer is 20% of total capacity |  | ? | 80
Actual buffer |  | 161.325 |  |  | Naresh, Parnapalli | 80
Total of Sprint 1, 2, 3, 4 - Dev + QA |  | 616
Daily scrum + bug fixes + devOps |  | 344.9
standard buffer |  | 261.6 | ~20% of total capacity
Total Capacity |  | 1308
Actual buffer |  | 347.1
Buffer % | 20
bug fixes + devOps (code review/review comments incorporation/build activties/BSA clarification) % | 35
UT % | 0.15

## BAU
ID | Title | State | Assigned To | Remaining Work | Iteration Path | Effort
1863854 | [Prod] EMA Mailbox sync issues | Committed | Vineeth Paul Geever |  | iConfirm\iConfirm 9.1.2 Release\iConfirm 9.1.2 Release - Sprint 3 | 60 |  |  |  | 1. mailboxes are not syncing: there is a job that runs every 10 mins to check if there is new email to sync in DB so that it is visible in iConfirm. If each GEO has 100+projects, EMA has issue, every few hrs we get email that mailbox is syncing 2. emails are missing from Inbox: mailbox has an attachment, we fetch data from outlook, download encrypted attachment, and save in DB, not getting saved in DB, emails not seen in iConfirm, not related to size, DB load | Console App: query emailbox, fetch attachment, try to encrpt and save to DB | partial solution in Feb release. End point URL. EWS team has given end points, end points are old and they missed to inform about new URLs. In stage its implemented. Only regression is done. Specific to EMA Pending stuff: Rishi grouped frequently occuring issues, EWS service is throwing errors, need to analyze
1876925 | [Prod] PDF attachments in emails synced in Iconfirm are not visible | Committed | Parnapalli Naresh |  | iConfirm\iConfirm 9.1.2 Release\iConfirm 9.1.2 Release - Sprint 3 | 18 |  |  |  | may be failing because of attachment | addressed by Consle app
1892914 | [Prod] Email not syncing to Project Inbox | Committed | Parnapalli Naresh | 33 | iConfirm\iConfirm 9.1.2 Release\iConfirm 9.1.2 Release - Sprint 3 | 45 |  |  |  | may be failing because of attachment | addressed by Consle app
1898950 | [Prod] Console App Utility | Committed | Parnapalli Naresh | 8 | iConfirm\iConfirm 9.1.2 Release\iConfirm 9.1.2 Release - Sprint 3 | 40
1899374 | [Prod] Iconfirm INC4574249 : Maintenance page | Done | Harish Kumar Anagandula |  | iConfirm\iConfirm 9.1.2 Release\iConfirm 9.1.2 Release - Sprint 3
1896188 | Iconfirm - remove a domain from restricted list | Committed | Antra Lnu | 8 | iConfirm\iConfirm 9.1.2 Release\iConfirm 9.1.2 Release - Sprint 3
1901285 | Iconfirm - Mailbox requires rename -9th Feb | Done | Antra Lnu |  | iConfirm\iConfirm 9.1.2 Release\iConfirm 9.1.2 Release - Sprint 3
1882710 | [Prod] Iconfirm - Automated set reminders not sending | Committed | Dolly Kumari |  | iConfirm\iConfirm 9.1.2 Release\iConfirm 9.1.2 Release - Sprint 3 | 30 | new PBI to track | awaiting pripiritization | Preeti should create PBI
1854596 | [Tech] Investigate the reason for locking during bulk inserts | Committed | Parnapalli Naresh | 5 | iConfirm\iConfirm 9.1.2 Release\iConfirm 9.1.2 Release - Sprint 3 | 50 |  |  | screen getting stuck when confirmation is sent. Deadlock issue, team found indexes missing, blocker is gone, indexes are in prod, from Jan start issue not reproducible, too many open connections though, based on bandwidth team can analyze | ON HOLD
Open as query

## POD Structure
Enhancement POD | Role | Prod Support | Role
Kumar Anagandula, Harish | Dev | Geever, Vineeth Paul | Dev
Surve, Diptesh Dattaram | Dev | Naresh, Parnapalli | Dev
Kumari, Dolly | Dev
Begum, Tadimarri Akhila | QA
Para, Mohsin Hussain | QA

## Timeline (hidden)
| dev start | dev completion | QA sign off UAT deployment | UAT sign off
Sprint 1
Sprint 2
Release QA Regression
UAT Regression

## PBIs Sprint 1
ID | Work Item Type | Title 2 | Iteration Path | Story Points | BE(Hr) | FE(Hr) | SQL(Hr) | UT | Dev + UT | Test Design | Test Execution | Dev + QA Estimate | Comments | Sprint | QA Deployment | Team assignment | Dev Start Date | Dev/UT Completion | Test cases start | Test cases completion | QA start | QA completion | QA Owner
1872472 | PBI | CCI - API changes to sync the CCI confirmations existing in Iconfirm |  |  | 45 | 0 | 0 | 6.75 | 51.75 | 4 | 6 | 61.75 |  |  |  | Diptesh
1846206 | PBI | CCI - API changes |  |  | 30 | 0 | 0 | 4.5 | 34.5 | 8 | 16 | 58.5 | sync confirmations.com, after a while, they disappear from iConfirm, don’t know the frequency |  |  | Harish
1898950 | PBI | Console App |  |  | 35 | 0 | 0 | 5.25 | 40.25 | 8 | 8 | 56.25 | dev in progress, app team |  |  | Naresh
Total | [7 empty] | 16.5 | 126.5 | 20 | 30 | 176.5

## PBIs Sprint 2
ID | Work Item Type | Title 2 | Iteration Path | Story Points | BE(Hr) | FE(Hr) | SQL(Hr) | UT | Dev + UT | Test Design | Test Execution | Dev + QA Estimate | Comments | Sprint | QA Deployment | Team assignment | Dev Start Date | Dev/UT Completion | Test cases start | Test cases completion | QA start | QA completion | QA Owner
1851132 | PBI | OPM Container Mapping Updates |  |  | 54 | 0 | 0 | 8.1 | 62.1 | 14 | 30 | 106.1 | Bolivia, Hungary, Gibraltar |  |  | Harish
1854595 | PBI | [Tech] Update Omnia links |  |  |  |  | 20 | 3 | 23 | 4 | 8 | 35 | no description and no AC, App team to update description, dacpac change |  |  | Dolly | [6 empty] | Akhila
1888098 | PBI | CCI - Change the ADFS authentication to AD authentication |  |  | 45 | 0 | 0 | 6.75 | 51.75 | 4 | 6 | 61.75 | no description, AC is present, Preeti to work with Harish to get description. Leverage technical discussion email with ADFS. Need to setup call with ADFS |  |  | Diptesh
Total | [7 empty] | 17.85 | 136.85 | 22 | 44 | 202.85

## PBIs Sprint 3
ID | Work Item Type | Title 2 | Iteration Path | Story Points | BE(Hr) | FE(Hr) | SQL(Hr) | UT | Dev + UT | Test Design | Test Execution | Dev + QA Estimate | Comments | Sprint | QA Deployment | Team assignment | Dev Start Date | Dev/UT Completion | Test cases start | Test cases completion | QA start | QA completion | QA Owner
1828981 | PBI | [Cookie management] [Tech] - Implement cookie banner |  |  | 37 | 0 | 0 | 5.55 | 42.55 | 16 | 16 | 74.55 |  |  |  | Naresh
1866451 | PBI | [Cookie management] - Provide Cookie Notice page |  |  | 16 | 0 | 0 | 2.4 | 18.4 | 8 | 8 | 34.4 |  |  |  | Dolly
1866461 | PBI | [Cookie management] - Add 'Manage Cookie Preferences' To User Settings |  |  | 8 | 0 | 0 | 1.2 | 9.2 | 8 | 8 | 25.2 |  |  |  | Harish
Total | [7 empty] | 9.15 | 70.15 | 32 | 32 | 134.15

## PBIs Sprint 4
ID | Work Item Type | Title 2 | Iteration Path | Story Points | BE(Hr) | FE(Hr) | SQL(Hr) | UT | Dev + UT | Test Design | Test Execution | Dev + QA Estimate | Comments | Sprint | QA Deployment | Team assignment | Dev Start Date | Dev/UT Completion | Test cases start | Test cases completion | QA start | QA completion | QA Owner
1885071 | PBI | [Prod] AME users getting directed to maintenance page |  |  | 0 | 0 | 40 | 6 | 46 | 6 | 16 | 68 | across GEOs. Update script. 70 container DBs |  |  | Dolly
1885803 | PBI | [Prod] PDF Generation Error |  |  | 30 | 0 | 0 | 4.5 | 34.5 | 0 | 0 | 34.5 | dev team to estimate, only AC is present |  |  | Diptesh
Total | [7 empty] | 10.5 | 80.5 | 6 | 16 | 102.5

## todo
ID | Type | Title | Action Item | Owner
1888098 | PBI | CCI - Change the ADFS authentication to AD authentication | Kunal to setup call with ADFS team to get details | Kunal
1854595 | PBI | [Tech] Update Omnia links | no description and no AC, App team to update description, dacpac change | Kunal
1885803 | PBI | [Prod] PDF Generation Error | estimates to be revised, description is missing | Marrisa
| PBI | Console App
issues
tasks not updated

## PBIs Sprint 3 old (hidden)
ID | Work Item Type | Title 2 | Iteration Path | Story Points | BE(Hr) | FE(Hr) | SQL(Hr) | UT | Dev + UT | Test Design | Test Execution | Dev + QA Estimate | Comments | Sprint | QA Deployment | Team assignment | Dev Start Date | Dev/UT Completion | QA Start | QA completion | QA Owner
|  | Hungary container rename |  |  | 2 |  |  |  | 2 | 4 | 4 | 10 |  | Sprint 3
|  | Cookie project | [6 empty] | 0 |  |  | 0 |  | Sprint 3
|  | Approved approach for Gibraltar removal |  |  | 2 |  |  |  | 2 | 4 | 4 | 10 |  | Sprint 3
|  | bug…830 | [6 empty] | 0 |  |  | 0 |  | Sprint 3
|  | perm fix | [6 empty] | 0 |  |  | 0 |  | Sprint 3
|  |  |  | 0 | 4 | 0 | 0 | 0 | 4 | 8 | 8 | 20
UT % |  | 0.15

## PBIs Sprint 2 old (hidden)
ID | Work Item Type | Title 2 | Iteration Path | Story Points | BE(Hr) | FE(Hr) | SQL(Hr) | UT | Dev + UT | Test Design | Test Execution | Dev + QA Estimate | Comments | Sprint | QA Deployment | Team assignment | Dev Start Date | Dev/UT Completion | QA Start | QA completion | QA Owner
|  | Enable browser caching of static files to increase performance |  |  | 24 | 0 | 0 | 3.6 | 27.6 | 0 | 36 | 63.6 |  | Sprint 2 | 2022-02-02 | Vaibhav | 2022-01-31 | 2022-02-02 | 2022-02-03 | 2022-02-08 | Ranjit/Anupam
| UST | Remove unused code |  |  | 18 | 9 | 9 | 5.4 | 41.4 | 0 | 0 | 41.4 |  | Sprint 2 | 2022-02-04 | Prathamesh | 2022-01-31 | 2022-02-04 | 2022-02-03 | 2022-02-08 | Ranjit/Anupam
|  | Enable appinsights for cron jobs | [9 empty] | 0 | may not have to implement. | Sprint 2
| UST | Upgrade Racer model to latest version (this library is used for real-time data synchronization) |  |  | 24 |  |  | 3.6 | 27.6 | 0 | 0 | 27.6 |  | Sprint 2 | 2022-02-03 | Prasad | 2022-01-31 | 2022-02-03 | 2022-02-03 | 2022-02-08 | Ranjit/Anupam
| UST | Implement localization for Template & Country manager screen | [5 empty] | 0 | 0 |  |  | 0 | Functional | Sprint 2
1857138 | Bug | Project count not updated | Scribe\Scribe 5.3.1 Release - Sprint 2 |  | 8 | 0 | 0 | 0 | 8 | 4 | 16 | 28 | dev testing | Sprint 2 | 2022-01-31 | Prasad | 2022-01-19 | 2022-01-19 | 2022-01-31 | 2022-02-02 | Anupam
1854752 | Bug | Ctrl Y and Ctrl Z do not work while editing deliverables | Scribe\Scribe 5.3.1 Release - Sprint 1 | [9 empty] | so far not reproducible - as of 01/17 | Sprint 2 |  | Raghu |  |  |  |  | Anupam
|  |  |  | 0 | 74 | 9 | 9 | 12.6 | 104.6 | 4 | 52 | 160.6
UT % |  | 0.15

## Sheet1 (hidden)
OPM access
ADO access
https://qscribe.deloitte.com/

## SP Estimation guidelines
As the story points represent the overall effort taken by the developers to create a story, the team should estimate the story point concerning all the factors that affect the effort of the developer. These include:
The amount of work that has to be done
The complexity of the task or work
Any uncertainty or risk while doing the work
These three factors have major impacts while estimating a story point.
Whats followed: Estimation Process of Planning Poker
T-shirt sizing method | SP | Complexity | SP | Tentative | ​Story Points | ​Time Frame | ​Example | hr | assumption | hr | assumption
X-Small | 1 | very simple | 1 | 4–12 hours | 1 | ​4 ideal hours | Changing text on a label | 4 | 6 hrs/day | 4 | 7 hrs/day
Small | 2 | simple | 2 | 10–20 hours | ​2 | 2-3 days, may require testing | ​Adding a new field | 12 to 18 | 6 hrs/day | 14 to 21 | 7 hrs/day
Medium | 3 | medium | 3 | 18-25 hours | ​3 | 4 days for 1 person | ​Adding a new field that may appear in a few places within the application | 24 | 6 hrs/day | 28 | 7 hrs/day
Large | 5 | complex | 5 | 25-40 hours | ​5 | 5 days for 1 person | ​Design and adding a section to an existing page | 30 to 40 | 6 hrs/day | 35 to 40 | 7 hrs/day
Extra-Large | 8 | Very Complex | 8 | 35-65 hours | ​8 | 10 days for 1 person | Design and add a new basic page | > 40 | 6 hrs/day | > 40 | 7 hrs/day
XXL | 13 | Very Very Complex | 13 | 60-90 hours | ​13 | ​15 days for 1 person | Avoid this, try to break it down
[5 empty] | ​20 | 1 month for 1 person | ​Way too big to be included in a sprint, break it down
[5 empty] | ​40 | 2 months for 1 person | Way too big to be included in a sprint, break it down